## Timeline
Time table for next HL survey EU
Date: 22.02.2018
Workpackages |  | Task | 0 Jahr | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
[15 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Interantional | M-POHL | (Organisation) Kick-Off meeting | bar: 2018 1 J to 2018 2 F; 2018 8 A
2nd f2f meeting | bar: 2018 8 A
3rd f2f meeting | bar: 2019 16 A to 2019 17 M
Organisation closing meeting | bar: 2020 35 N to 2020 36 D
| Preparation survey | Definition of work packages | bar: 2018 2 F to 2018 8 A
Agreement on work package leaders | bar: 2018 2 F to 2018 8 A
Preparation study protocol (study design , instrument, data collection) | bar: 2018 2 F to 2018 6 J
Preparation of financial plan | bar: 2018 2 F to 2018 6 J
Agreement on general study protocol incl. condictions for participation | bar: 2018 8 A
Agreement on general financial plan | bar: 2018 8 A
Finetuning of study protocol/instument | bar: 2018 9 S to 2019 16 A
Preparation of the pre-test | bar: 2018 11 N to 2018 12 D
Conducting pre-test | bar: 2019 13 J to 2019 14 F
Agreement on definite study protocol | bar: 2019 15 M to 2019 16 A
Translation of instrument | bar: 2019 17 M to 2019 21 S
Ethical approval(s)?? | bar: 2019 13 J to 2019 17 M
Contracting institution(s) for data collection | bar: 2019 17 M to 2019 19 J
| Data collection | Data collection (field time) | bar: 2019 22 O to 2020 26 F
Finalisation data set | bar: 2019 23 N to 2020 27 M
| Finalisation and reporting | Internat. analysis and reporting | bar: 2020 28 A to 2020 32 A
Dissemination, final conference/meeting | bar: 2020 31 J to 2020 36 D
| Int. Coordination | Coordination/dissemination/ (preparation) e-meetings
National | M-POHL | Kick-off meeting | bar: 2018 1 J to 2018 2 F
| Preparation survey | Kick-off national steering groups | bar: 2018 3 M to 2018 5 M
Definition national priorities, target group(s) | bar: 2018 3 M to 2018 8 A
Fundraising | bar: 2018 8 A to 2018 12 D
Contracting national study centre | bar: 2019 13 J to 2019 19 J
| Data collection | Data collection (field time) | bar: 2019 22 O to 2020 26 F
Finalisation data set | bar: 2019 23 N to 2020 27 M
| Finalisation and reporting | National analysis and reporting (quality assurance) | bar: 2020 30 J to 2020 34 O
| National Coordination | Coordination/dissemination/ (preparation) e-meetings

## national (hidden)
Workpackages |  | Task | 0 Jahr | [11 empty] | year 1 | [11 empty] | year 2 | [11 empty] | year 3
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
[15 empty] | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
| M-POHL | Aufbau Projektbeirat, Rekrutierung Mitarbeiter | bar: year 1 1 J to year 1 3 M
Kick-Off Meeting | bar: year 1 3 M
| Preparation study | Studie/Instrument/Forschungsfragen | bar: year 1 4 A to year 1 11 N
| Daten- | Erhebung/Feldzeit* | bar: year 1 12 D to year 2 14 F; year 3 25 J to year 3 26 F
| erhebung | Finalisierung Datensatz | bar: year 2 14 F to year 2 15 M; year 3 26 F to year 3 27 M
| Abschluss | Nationale Analyse und Berichterstattung | bar: year 2 16 A to year 2 20 A; year 3 28 A to year 3 32 A
Dissemination | bar: year 2 21 S to year 2 24 D; year 3 33 S to year 3 36 D